DAIRY FARM APP

# Project Proposal
& Cost Estimation

Based on the client's application menu and feature list

| Proposal detail | Value |
| --- | --- |
| Prepared for | Party 1 |
| Prepared by | Party 2 |
| Proposal date | 10 October 2026 |
| Estimate validity | 30 days from proposal date |

PROVISIONAL ESTIMATE

Estimated cost: ₹60,000  |  Estimated timeline: 5 – 7 weeks

# 1. Executive Summary

This   proposal is based on the menu options shown in the supplied Dairy Farm Project notes. The application is organized into three business areas: Your Dairy, Milk to Market, and Business. It covers farm/herd management, milk production and processing operations, inventory and finance, employees, compliance records, and reporting. The estimate assumes a mobile application with a newly developed backend and database, delivered by a small development team.

The budget and schedule below are provisional planning estimates. Detailed workflows, calculations, user roles, device/platform requirements, report formats, integrations, data volumes, and compliance expectations must be confirmed before a fixed-price contract is signed.

# 2. Application Menu & Proposed Scope

Menu options and access below are proposed. Final permissions must be confirmed with the client; one person may hold multiple roles.

| Menu group | Menu option | Primary users | Proposed functionality / scope |
| --- | --- | --- | --- |
| A. Your Dairy | Overview | Farm Owner/Super Admin; Farm Manager | Farm KPIs, herd count, milk yield, health alerts, upcoming calving/vaccination and key costs. Exact dashboard indicators and formulas to be approved. |
| A. Your Dairy | Herd & Calves | Farm Owner; Farm Manager; Herd/Animal Care Staff | Animal profiles and identifiers, breed, age/sex, status, calf records and animal history. |
| A. Your Dairy | Milking Log | Farm Owner; Farm Manager; Milking Staff | Daily milking entries by animal/group, date and shift; quantity tracking and history. Hardware integration excluded. |
| A. Your Dairy | Health & Vaccination | Farm Owner; Farm Manager; Herd/Animal Care Staff | Health events, treatment notes, vaccination schedules, due dates and history. Not a veterinary diagnosis system. |
| A. Your Dairy | Breeding & Calving | Farm Owner; Farm Manager; Herd/Animal Care Staff | Breeding/insemination records, pregnancy follow-ups, expected calving dates, outcomes and animal history. |
| A. Your Dairy | Feed & Ration Planning | Farm Owner; Farm Manager; Herd/Animal Care Staff | Feed ingredients, ration plans, consumption entries and estimated feed costs. Nutrition formulas to be confirmed. |
| A. Your Dairy | Unit Costing | Farm Owner; Farm Manager; Accountant/Finance | Configurable costing inputs and estimated cost per unit, such as cost per litre, using client-approved formulas. |
| B. Milk to Market | BMC & Milk Intake | Farm Owner; Farm Manager; Milk Intake/BMC Operator | BMC intake records, source, quantity, date/shift and intake summaries. Automated equipment integration excluded. |
| B. Milk to Market | Production Batches | Farm Owner; Production Operator; Quality Control Staff | Batch creation/tracking from intake to finished output, batch references and yield records. |
| B. Milk to Market | Packaging | Production Operator; Storekeeper; Farm Manager | Product/packaging types, pack sizes, quantities and packaging activity. Label-printer integration excluded. |
| B. Milk to Market | Quality Records | Quality Control Staff; Farm Manager; Read-only Auditor | Agreed quality parameters, inspections, batch linkage and quality history. Lab equipment integration excluded. |
| B. Milk to Market | Material Issues | Production Operator; Storekeeper; Farm Manager | Materials issued to production/packaging, quantities, batches/recipients and stock movements. |
| B. Milk to Market | Electricity Readings | Production Operator; Farm Manager; Accountant (view) | Manual meter readings and consumption summaries where opening/closing reading rules are defined. |
| B. Milk to Market | Orders & Dispatch | Sales/Dispatch Staff; Farm Manager | Customer orders, order status, dispatch details, quantities and dispatch history. |
| B. Milk to Market | Sales | Sales/Dispatch Staff; Accountant; Farm Manager | Sales entries, product/quantity/price and agreed sales summaries. Statutory e-invoicing excluded. |
| B. Milk to Market | Customer Payments | Accountant/Finance; Sales Staff (limited); Farm Owner | Payment entries, outstanding balances, payment history and basic receivable summaries. |
| C. Business | Common Inventory | Storekeeper; Farm Manager; Farm Owner | Shared stock items, units, stock-in/stock-out, balances, reorder indicators and inventory history. |
| C. Business | Biogas Fertiliser | Farm Manager; Assigned Operator; Accountant (view) | Biogas/fertiliser output, quantities, usage or sales and related records. Plant sensors/automation excluded. |
| C. Business | Wastage & Losses | Storekeeper; Production Operator; Farm Manager | Wastage/loss type, quantity, reason, date and related batch/inventory reference. |
| C. Business | Costs & Expenses | Accountant/Finance; Farm Owner; Farm Manager (limited) | Expense categories, transactions, dates, notes and operating-cost summaries. |
| C. Business | Employees | HR/Employee Administrator; Farm Owner; Farm Manager (limited) | Employee profiles, contact details, roles and employment status. Salary/personal data restricted to authorized users. |
| C. Business | FSSAI & Licences | Farm Owner; Farm Manager; Compliance/Read-only Auditor | Licence details, numbers, issue/expiry dates and reminders. Filing/renewal services excluded. |
| C. Business | Reports & Exports | Farm Owner; Farm Manager; Accountant; authorized role owners | Agreed operational reports and CSV/Excel exports where supported, limited by user permissions. |
| C. Business | Farm Settings | Farm Owner/Super Admin only | Farm profile, master data, units, preferences and user/role settings. |
| Platform & Services | Mobile App, Backend & Database | All users according to role; Super Admin administers | Authentication, role permissions, APIs/database, validation, error handling, integration, testing, release build and handover. |

## 2.1 Recommended User Roles & Access

These are logical roles, not a requirement for 11 separate employees. Use individual accounts and role-based permissions (view, create, edit, approve, export, administer).

| Recommended role | Access summary |
| --- | --- |
| Farm Owner / Super Admin | All modules; manage users/roles, farm settings, permissions, approvals and full reports. |
| Farm Manager | Day-to-day farm operations and approved access to herd, milk, production, stock, expenses and reports. |
| Herd / Animal Care Staff | Herd & Calves, Milking Log, Health & Vaccination, Breeding & Calving, Feed & Ration Planning. |
| Milk Intake / BMC Operator | BMC & Milk Intake and permitted intake records. |
| Production / Packaging Operator | Production Batches, Packaging, Material Issues and assigned production records. |
| Quality Control Staff | Quality Records and related batch-quality history. |
| Storekeeper / Inventory Staff | Common Inventory, stock receipts/issues, material availability and wastage records. |
| Sales / Dispatch Staff | Orders & Dispatch, Sales and limited customer/payment lookup. |
| Accountant / Finance Staff | Customer Payments, Costs & Expenses, Unit Costing and financial reports/exports. |
| HR / Employee Administrator | Employee records and, if separately approved, attendance records. |
| Read-only Auditor / Consultant (optional) | View selected reports and records without creating or editing transactions. |

## 2.2 Technology Stack (Proposed)

| Layer | Selected technology | Purpose / notes |
| --- | --- | --- |
| Mobile application | Flutter (Dart) | Cross-platform mobile app codebase for Android; iOS can be supported if included in the agreed scope. |
| Backend / API server | Node.js with NestJS | Develop REST APIs, business logic, modular services, and backend functionality. |
| Database | MySQL | Stores farm, animal, milk, production, inventory, payments, employee, and reporting data. |
| Authentication & authorization | JWT-based authentication with role-based access control | Individual user sign-in and permissions for Farm Owner, Manager, Operators, Finance, Inventory, and other approved roles. |
| API documentation & testing | Swagger / OpenAPI where appropriate; Postman | Document and test backend API endpoints. |
| Hosting & deployment | Cloud/VPS hosting for Node.js API and MySQL | Production environment, environment variables, SSL, database backups, and monitoring. Hosting charges are separate. |
| Push notifications (optional) | Firebase Cloud Messaging | Optional app notifications for vaccination, calving, licence expiry, or stock alerts. Confirm requirements and setup. |
| Source control & releases | Git; CI/CD if agreed | Version control and release process; repository access and ownership to be agreed in the contract. |

## Technology and scope assumptions

The client must confirm Android-only versus Android and iOS delivery. The existing proposal says mobile app, but the uploaded proposal and menu notes do not prove a specific framework or backend technology.

Offline entry and synchronization, payment gateway/bank integration, hardware integrations, biometric/GPS attendance, SMS/WhatsApp, advanced accounting/tax integrations, and data migration are not included unless separately scoped.

Hosting, domain, app-store fees, paid third-party services and messaging charges are separate from development cost.

# 3. Estimated Timeline

| Phase | Activities | Duration |
| --- | --- | --- |
| 1 | Requirement workshops, workflows and scope sign-off | 3 - 5 days |
| 2 | UI/UX screens and client approval | 7 - 10 days |
| 3 | Backend, database, login, roles and app foundation | 4 - 5 days |
| 4 | Your Dairy modules | 3 – 5 days |
| 5 | Milk to Market modules | 3 – 5 days |
| 6 | Business modules and reports/exports | 3 – 5 days |
| 7 | Integration, QA, UAT, fixes and release/handover | 7 – 10 days |

Overall estimated duration: 5 – 7 weeks from kickoff, receipt of the advance, and availability of approved requirements. Some phases may overlap. Delays in client feedback, scope changes, data migration, third-party services, or device integration can affect delivery.

# 4. Payment Milestones

| Milestone | Share | Amount | Trigger |
| --- | --- | --- | --- |
| Kickoff and scope confirmation | 20% | ₹12,000 | Before development starts |
| UI/UX and foundation approval | 30% | ₹18,000 | After design and core foundation demonstration |
| Core module completion | 30% | ₹18,000 | After agreed modules are available for client testing |
| UAT completion, release and handover | 20% | ₹12,000 | After agreed acceptance criteria and handover |
| TOTAL | 100% | ₹60,000 | Taxes and approved extras are additional |

Estimate note: costs are indicative and depend on detailed acceptance criteria. This is a moderate-complexity baseline for the listed menu options, not a guarantee that every advanced workflow or integration is included. Applicable taxes, hosting, domain, app-store fees, paid services, messaging fees, hardware, and third-party subscriptions are additional.

# 5. Scope Assumptions & Items to Confirm

Platform: this estimate assumes an Android-first mobile application. Confirm whether iOS is also required and whether the app will be built cross-platform or natively.

User types and permissions: farm owner/manager, veterinary/animal-care staff, milk collection/processing staff, sales/accounts, inventory, and employees are examples only; final roles must be approved.

Offline usage: reliable offline data entry and synchronization are not included unless explicitly specified. Farm locations with weak connectivity may make this requirement important.

Calculations: milk yield, unit costing, ration cost, production yield, stock valuation, wastage, expenses, and balances depend on client-approved formulas and rules.

Quality records: the client must specify which quality parameters are tracked, such as fat/SNF or other tests. Laboratory/analyzer integrations are excluded.

Reports: report names, filters, date ranges, summaries, and export columns must be listed and approved during discovery.

Data migration: historical data import from registers, spreadsheets, or existing software is excluded until the format and volume are assessed.

Client will provide branding, operational rules, sample forms/registers, product and unit definitions, licence information, and timely feedback.

# 6. Exclusions (Unless Quoted Separately)

iOS support if not confirmed in the final platform scope; web admin panel or separate desktop application.

Direct integrations with BMC equipment, milk analyzers, weighing scales, IoT sensors, packaging/label printers, biometric devices, or electricity meters.

Payment gateway/bank integrations, GST/e-invoicing, full accounting/ERP, payroll, statutory filing, licence application/renewal, and legal/veterinary advice.

Automated nutritional/veterinary recommendations, advanced forecasting/AI, route optimization, GPS tracking, or advanced offline synchronization.

SMS/WhatsApp/email provider charges, cloud hosting, domain, app-store fees, paid licences, backup/storage costs, and other third-party subscription charges.

Bulk historical data cleansing/import, extensive multilingual translation, custom hardware procurement, and new features outside the approved scope.

# 7. Testing, Acceptance & Handover

The team will test the application against approved requirements and provide a build for user acceptance testing (UAT). The client should report reproducible defects within the agreed UAT window. Handover will include the release build, setup/configuration notes, basic user walkthrough, and source code as defined in the signed agreement. Source-code ownership and transfer terms must be stated in the contract and may be subject to full payment.

# 8. Maintenance & Support

| Item | Proposed terms |
| --- | --- |
| Defect warranty | 90 days after production handover for reproducible defects in agreed delivered features, excluding issues caused by third-party changes, misuse, or unauthorized modifications. |
| Optional support plan | Indicative ₹5,000–₹10,000 per month depending on support hours, response times, monitoring, backup responsibilities, and minor-change allowance. A separate SLA is required. |
| Not covered by warranty | New features, changes in business rules, third-party outages/fees, hosting bills, operating-system changes requiring substantial rework, or support for systems modified by others. |
| Cloud and third-party costs | Paid by the client directly where possible, or charged at actual cost with prior written approval. |

# 9. Change Control & Commercial Terms

Any functionality outside the approved scope must be documented in a written change request, including cost and schedule impact, before work starts.

The schedule depends on timely client approvals, access to information, and payment of milestones.

Third-party service pricing, uptime, and approval times are controlled by their providers and cannot be guaranteed by the development team.

This proposal is valid for 30 days and is not a final contract. The final statement of work must confirm platform(s), detailed workflows, acceptance criteria, taxes, hosting, intellectual-property rights, confidentiality, and support terms.

# 10. Approval

If the proposed scope, provisional budget, and timeline are acceptable, the next step is a requirement-discovery session to finalize the statement of work.

| Client approval | Development team approval |
| --- | --- |
| Name: __________________________ | Name: __________________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

Thank you for considering this proposal.